Week 1: 21 Jan – 27 Jan | ROS2 & Gazebo Foundations

Goal: Get comfortable with ROS2 and launch a basic UR7e in Gazebo.

| Day | Task |
| --- | --- |
| Wed–Thu | Install ROS2 (Humble/Iron), Gazebo, UR ROS2 packages, MoveIt2. Follow official ROS2 beginner tutorials (nodes, topics, launch files). |
| Fri | Clone UR7e ROS2 packages; launch UR7e URDF in Gazebo. Verify joint state topics publishing. |
| Sat–Sun | Write a minimal Python ROS2 node that sends joint velocity commands to the simulated arm. Record a short rosbag of the motion. |
| Ongoing | Set up COMP303 GitHub branch; create development log markdown file (required for assessment). |

Week 2: 28 Jan – 3 Feb | RL Environment Wrapper

Goal: Build the Gym-style environment around Gazebo UR7e.

| Day | Task |
| --- | --- |
| Wed–Thu | Design observation space (joint angles, end-effector pose, goal position) and action space (discrete for Q-Learning, continuous for PPO) as per your proposal. |
| Fri–Sat | Implement custom Gym environment: reset(), step(action), reward function (goal +ve, collision –ve, timestep penalty). |
| Sun | Add Gazebo contact sensor for collision detection; expose as ROS2 topic and integrate into environment's step() return. |

Week 3: 4 Feb – 10 Feb | Q-Learning Integration & Debugging

Goal: Port your existing Q-Learning script into the ROS2/Gazebo pipeline.

| Day | Task |
| --- | --- |
| Wed–Thu | Adapt your existing Q-Learning code to use the new Gym environment wrapper. Ensure discrete action mapping matches UR7e joint velocity increments. |
| Fri | Add CSV logging: episode number, collisions, completion time, total reward, steps – matching your R analysis script format. |
| Sat–Sun | Run 100–200 episode smoke test. Debug any issues (sim resets, action clamping, reward scaling). Verify CSV output is correct. |

Week 4: 11 Feb – 17 Feb | PPO Implementation

Goal: Implement PPO from scratch (or using Stable-Baselines3) and validate it.

| Day | Task |
| --- | --- |
| Wed–Thu | Implement PPO in PyTorch: actor-critic networks, clipped surrogate objective, GAE advantage estimation. Alternatively, set up Stable-Baselines3 PPO with your custom env. |
| Fri | Ensure observation/action spaces and reward function are identical to Q-Learning setup for fair comparison. |
| Sat–Sun | Run pilot PPO training (200–500 episodes). Check loss curves, average reward improvement. Add unit tests for tensor shapes and gradient flow. |

Week 5: 18 Feb – 24 Feb | Maze Design & End-Effector Fabrication

Goal: Design and start printing the physical maze and sensor end-effector.

| Day | Task |
| --- | --- |
| Wed–Thu | Design 3D-printed maze in Fusion 360 (narrow corridors to stress precision as per proposal). Export STL. |
| Fri | Design custom end-effector with piezo sensor mount. Export STL. Send both for printing. |
| Sat | Wire piezo sensor to Arduino Nano; write ROS2 node to publish binary collision topic. Bench-test off-robot. |
| Sun | Import maze geometry into Gazebo as collision mesh. Update environment to use maze world. |

Week 6: 25 Feb – 3 Mar | Full Simulation Training

Goal: Run complete training for both algorithms with domain randomisation.

| Day | Task |
| --- | --- |
| Wed–Thu | Implement domain randomisation (friction, joint damping, small maze pose variations) as described in proposal. |
| Fri–Sat | Run full Q-Learning training until convergence (use rolling average reward threshold from your R appendix). Log all episodes. |
| Sun | Run full PPO training. Compare convergence speed. Save best model checkpoints for both algorithms. |

Week 7: 4 Mar – 10 Mar | Hardware Integration (Low-Risk Trials)

Goal: Mount maze on real UR7e and run initial validation trials.

| Day | Task |
| --- | --- |
| Wed | Work with lab technician: mount maze fixture and end-effector on UR7e. Verify workspace fit and safety limits. |
| Thu–Fri | Run 5–10 slow-speed trials per algorithm under supervision. Confirm piezo collision detection fires correctly. Check rosbag and CSV logs. |
| Sat–Sun | Refine safety timeouts, speeds, and joint limits based on dry runs. Document any protocol amendments in ethics/dev log. |

Week 8: 11 Mar – 17 Mar | Main Hardware Experiment (80 Trials)

Goal: Collect all experimental data on the physical UR7e.

| Day | Task |
| --- | --- |
| Wed–Thu | Execute 40 Q-Learning trials on real UR7e using standardised start config and termination conditions. |
| Fri–Sat | Execute 40 PPO trials under identical conditions. |
| Sun | Backup all rosbags and CSVs. Mark invalid trials for exclusion; schedule replacement trials if needed to maintain ≥40 valid per algorithm. Export consolidated experiment_results.csv. |

Week 9: 18 Mar – 24 Mar | Statistical Analysis

Goal: Run complete statistical analysis as per your proposal.

| Day | Task |
| --- | --- |
| Wed–Thu | Run MANOVA for global hypothesis (H1). Run independent t-tests for collisions, completion time, convergence episodes (H1a–H1c). |
| Fri | Run correlation analysis between time and collision count (H1d). Check assumptions (normality, homogeneity); use non-parametric alternatives if violated. |
| Sat–Sun | Generate publication-ready tables and figures: means, SDs, confidence intervals, learning curves, box plots. |

Week 10: 25 Mar – 31 Mar | Dissertation Writing (Results & Discussion)

Goal: Draft the core results and discussion sections.

| Day | Task |
| --- | --- |
| Wed–Thu | Write Results section: insert tables, figures, p-values, effect sizes. State clearly whether each hypothesis was supported. |
| Fri–Sat | Write Discussion section: interpret findings for safety, efficiency, learning speed. Discuss sim-to-real transfer performance and domain randomisation impact. |
| Sun | Update Methods section from proposal to reflect actual implementation. Ensure artefact design section matches final code. |

Week 11: 1 Apr – 7 Apr | Dissertation Completion & Addenda

Goal: Complete full manuscript including all required addenda.

| Day | Task |
| --- | --- |
| Wed–Thu | Write/update Introduction, Background, Literature Review (adapt from proposal). Write Conclusion with explicit contributions. |
| Fri | Write 1–2 page reflective addendum: what went well, what slipped, lessons learned. |
| Sat | Finalise statistics addendum (clean R/Python code that reproduces all results from raw CSV). Finalise test plan addendum with unit/integration/system test results. |
| Sun | Send full draft to supervisor. Request feedback by Monday/Tuesday. |

Week 12: 8 Apr – 14 Apr | Final Polish & Submission

Goal: Incorporate feedback, polish, and submit.

| Day | Task |
| --- | --- |
| Wed–Thu | Incorporate supervisor feedback. Final proof-read for consistency between text, figures, and repository. |
| Fri | Ensure IEEE/ACM formatting is correct. Verify all references are accurate and complete. Trim/expand to fit 12-page limit (excluding figures, tables, refs, appendices). |
| Sat–Sun | Tag and release final computing artefact on GitHub with source code, trained models, launch files, and demo video. |
| Tue 14 Apr | Submit dissertation PDF to LearningSpace before deadline. |

Viva Preparation: 14 Apr – 16 Apr

| Day | Task |
| --- | --- |
| Tue (post-submission) | Build 15-minute presentation: purpose, approach, artefact demo (video clips of PPO vs Q-Learning), statistical results, ethical considerations. |
| Wed 15 Apr | Rehearse presentation with timer. Prepare for 5-min Q&A on methodology, results interpretation, and limitations. |
| Thu 16 Apr | Deliver viva presentation. |

Weekly Hour Estimate

Based on the ~200 hours expected for COMP303 (20 credits), this breaks down to approximately 17 hours/week across 12 weeks. Adjust based on other module commitments.

| Phase | Weeks | Focus |
| --- | --- | --- |
| Learning & Setup | 1–2 | ROS2, Gazebo, environment wrapper |
| Implementation | 3–4 | Q-Learning integration, PPO from scratch |
| Hardware Prep | 5 | Maze, end-effector, piezo sensing |
| Training & Transfer | 6–7 | Full sim training, domain randomisation, hardware integration |
| Data Collection | 8 | 80 trials on real UR7e |
| Analysis & Writing | 9–11 | Statistics, full dissertation draft |
| Polish & Submit | 12 | Final revisions, submission, viva prep |